## Sheet1
|  | PREPARATORY |  |  |  | SOFTWARE CODING | [7 empty] | REPORTING
Date | Week | 1.1&1.2 | 1.3&1.4 | 1.5&1.6 | 1.8 | [8 empty] | 3.1 | 3.2 | 3.3 | 3.4&3.5
2019-10-19 | 1 | Meeting
2019-10-20 | 2 | Proposal
2019-10-27 | 3 | RevisePp | PA1 | WB
2019-11-03 | 4 |  |  |  |  | 2.1&2.2
2019-11-10 | 5 |  | DPP/PA2 | SPP1 |  | Data analysis | [9 empty] | DP1
2019-11-17 | 6
2019-11-24 | 7 |  |  | PMPC |  |  | 2.3
2019-12-01 | 8 |  |  |  | PD1 |  | Colerration analysis | [6 empty] | IR |  |  | PD1
2019-12-08 | 9 | [13 empty] | IR
2.4
2019-12-15 | 10 | [7 empty] | Implement model
2019-12-22 | 11
2019-12-29 | 12
2020-01-05 | 13 |  |  | SPP2
2020-01-12 | 14 |  |  |  | PD2 | [11 empty] | PD2
2020-01-19 | 15
2020-01-26 | 16
2020-02-02 | 17 | [8 empty] | 2.5 |  | 2.7
2020-02-09 | 18 | [8 empty] | Training |  | UI code |  |  |  | DP2
2020-02-16 | 19 | [9 empty] | 2.6
2020-02-23 | 20 |  |  | SPP3 | [6 empty] | Adjust&select
2020-03-01 | 21 | [10 empty] | 2.8
2020-03-08 | 22 | [10 empty] | Generalize
2020-03-15 | 23 | [11 empty] | 2.9
2020-03-22 | 24 |  |  |  | FD | [7 empty] | Testing |  |  |  | FD
2020-03-29 | 25 | [12 empty] | DD
2020-04-05 | 26 | [15 empty] | DS
2020-04-12 | 27
2020-04-19 | 28 | [15 empty] | DD
ADMINISTRATIVE DELIVERABLES | [7 empty] | INTERIM DELIVERABLES
2019-10-19 | SAF | Supervisor agreement form | [5 empty] | DP1/2 | Dissertation plan and schedule
2019-10-22 | PP | Project proposal | [5 empty] | PD1/2 | Preliminary draft (structure)
2019-10-24 | RPP | Revised project proposal | [5 empty] | FD | First draft
2019-10-26 | PPC | Prepare project charter | [5 empty] | PMCP | Process monitoring and control plan
2019-10-31 | WB | Group website site up | [5 empty] | PA | Project assumption
2019-12-12 | IR | Interim reports due | [5 empty] | DPP | Develop project plan
2020-04-09 | DS | Final reports and software due | [5 empty] | SPP | Software project plan
2018-04-22 | DD | Presentation Day (TBC) | [5 empty] | SDF | Standardized data format
[8 empty] | DDI | Database design and implementation
[8 empty] | DAS | Data analytics software
[8 empty] | IS | Integrate system
[8 empty] | STV | Software development
[8 empty] | DEMO | Demonstration
[8 empty] | PR | Prototype
[8 empty] | RT | Rapid test